## Actions
Action # | Committee | Action | Description | Parties Responsible | Tangible/Intangible | Team Project Manager | Initial Target Delivery Date | Endorsed by Mayor | Progress | Count | Key/Standard
1 | Building Public Safety | Create Mayor's Office of Neighborhood Safety and Engagement. |  | MONSE | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Key
2 | Building Public Safety | Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. |  | BPD | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Standard
3 | Building Public Safety | Set clear, coordinated public safety vision that addresses violence today and root causes. |  | MO, MONSE, BCHD, BPD | Tangible | TBD | 2021-02-01 | TBD | In progress | 1 | Key
4 | Building Public Safety | Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. |  | MONSE | Tangible | TBD | 2021-02-01 | TBD | In progress | 1 | Standard
5 | Building Public Safety | Introduce local housing voucher program. |  | DHCD | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
6 | Building Public Safety | Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. |  | DOT | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
7 | Making Baltimore Equitable | Hire Baltimore's first Chief Equity Officer. |  | MO, ECR | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Key
8 | Making Baltimore Equitable | Identify a senior official in each agency to be responsible for equity and sustainable action. |  | MO | Tangible | TBD | 2021-02-02 | TBD | In progress | 1 | Standard
9 | Making Baltimore Equitable | Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. |  | MO, DOP | Tangible | TBD | 2021-02-03 | TBD | Not yet started | 1 | Key
10 | Making Baltimore Equitable | Elevate Sustainability Director to a cabinet-level position. |  | MO, DOP | Intangible | TBD | 2021-02-04 | TBD | Not yet started | 1 | Standard
11 | Making Baltimore Equitable | Remove the most vulnerable residents from tax sale. |  | DOF | Intangible | TBD | 2021-02-05 | TBD | Not yet started | 1 | Standard
12 | Making Baltimore Equitable | Announce a back-to-basics community development strategy that centers community input. |  | MO, DHCD | Tangible | TBD | 2021-02-06 | TBD | Not yet started | 1 | Standard
13 | Making Baltimore Equitable | Activate small and local business preference in the procurement process. |  | DOF, BOP | Tangible | TBD | 2021-02-07 | TBD | Not yet started | 1 | Key
14 | Making Baltimore Equitable | Prioritize the Baltimore Greenway Trails Network. |  | DOP, DOT, DRP | Intangible | TBD | 2021-02-08 | TBD | Not yet started | 1 | Standard
15 | Prioritizing Our Youth | Support the overrides of the Blueprint for Maryland's Future and Built to Learn. |  | MO, MGA | Intangible | TBD | 2021-02-09 | TBD | Not yet started | 1 | Key
16 | Prioritizing Our Youth | Prepare to significantly increase the capacity of virtual YouthWorks in 2021. |  | MOED | Intangible | TBD | 2021-02-10 | TBD | Not yet started | 1 | Standard
17 | Prioritizing Our Youth | Begin implementation and allocate funding to the Elijah Cummings Healing City Act to ensure trauma-informed practice. |  | BCHD, MONSE | Tangible | TBD | 2021-02-11 | TBD | Not yet started | 1 | Standard
18 | Prioritizing Our Youth | Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. |  | DRP | Tangible | TBD | 2021-02-12 | TBD | Not yet started | 1 | Standard
19 | Building Public Trust | Hire Baltimore's first Chief Administrative Officer. |  | MO | Tangible | TBD | 2021-02-13 | TBD | Complete | 1 | Key
20 | Building Public Trust | Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. |  | MO | Tangible | TBD | 2021-02-14 | TBD | In progress | 1 | Standard
21 | Building Public Trust | Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. |  | OPI | Tangible | TBD | 2021-02-15 | TBD | Not yet started | 1 | Key
22 | Building Public Trust | Restore recycling services, which were suspended due to COVID-19. |  | DPW | Tangible | TBD | 2021-02-16 | TBD | Not yet started | 1 | Standard
23 | Building Public Trust | Announce plan to reform the water billing program. |  | DPW | Tangible | TBD | 2021-02-17 | TBD | Not yet started | 1 | Standard
24 | Building Public Trust | Appoint a permanent Housing Commissioner. |  | DHCD | Tangible | TBD | 2021-02-18 | TBD | Not yet started | 1 | Standard
25 | Building Public Trust | Appoint a permanent Homeless Services director. |  | MOHS | Tangible | TBD | 2021-02-19 | TBD | Not yet started | 1 | Key
26 | Building Public Trust | Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. |  | DPW, DOT | Tangible | TBD | 2021-02-20 | TBD | Not yet started | 1 | Standard
27 | Building Public Trust | Make stronger commitments to cleaning up sewage backups. |  | DPW |  |  |  |  | Not yet started | 1 | Standard
28 | COVID-19 Recovery | Develop and communicate a COVID-19 vaccination prioritization strategy. |  | BCHD |  |  |  |  | Not yet started | 1 | Standard
29 | COVID-19 Recovery | Create a dashboard to track CARES act funding to ensure equitable distribution. |  | DOF |  |  |  |  | Not yet started | 1 | Standard
30 | COVID-19 Recovery | Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. |  | MOHS |  |  |  |  | Not yet started | 1 | Standard
31 | COVID-19 Recovery | Extend emergency shelter in local hotels when CARES Act funding expires. |  | MOHS |  |  |  |  | Not yet started | 1 | Standard
32 | COVID-19 Recovery | Cap restaurant delivery fees on third-party app services. |  | DOF |  |  |  |  | In progress | 1 | Standard
33 | COVID-19 Recovery | Identify clear point of contact for local businesses to more effectively navigate city government. |  | MO, BDC |  |  |  |  | Not yet started | 1 | Standard
34 | Responsible Stewardship of City Resources | Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. |  | DGS |  |  |  |  | Not yet started | 1 | Standard
35 | Responsible Stewardship of City Resources | Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. |  | DOF |  |  |  |  | Not yet started | 1 | Standard
36 | Responsible Stewardship of City Resources | Announce new criteria for evaluation of capital budget requests. |  | MO, DOF |  |  |  |  | Not yet started | 1 | Standard
37 | Responsible Stewardship of City Resources | Design and release Open Checkbook for Baltimore to increase transparency and accountability. |  | BCIT, DOF |  |  |  |  | Not yet started | 1 | Standard

## Days
100 Days of Action (From Launch) | 2021 First 100 Days Number | Mayoral First 100 Days Number | Date | Weekday | Milestone? | Notes?
|  | 1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
|  | 2 | 2020-12-09 | 2020-12-09
|  | 3 | 2020-12-10 | 2020-12-10
|  | 4 | 2020-12-11 | 2020-12-11
|  | 5 | 2020-12-12 | 2020-12-12
|  | 6 | 2020-12-13 | 2020-12-13
|  | 7 | 2020-12-14 | 2020-12-14
|  | 8 | 2020-12-15 | 2020-12-15
|  | 9 | 2020-12-16 | 2020-12-16
|  | 10 | 2020-12-17 | 2020-12-17
|  | 11 | 2020-12-18 | 2020-12-18
|  | 12 | 2020-12-19 | 2020-12-19
|  | 13 | 2020-12-20 | 2020-12-20
|  | 14 | 2020-12-21 | 2020-12-21
|  | 15 | 2020-12-22 | 2020-12-22
|  | 16 | 2020-12-23 | 2020-12-23
|  | 17 | 2020-12-24 | 2020-12-24
|  | 18 | 2020-12-25 | 2020-12-25
|  | 19 | 2020-12-26 | 2020-12-26
|  | 20 | 2020-12-27 | 2020-12-27
|  | 21 | 2020-12-28 | 2020-12-28
|  | 22 | 2020-12-29 | 2020-12-29
|  | 23 | 2020-12-30 | 2020-12-30
|  | 24 | 2020-12-31 | 2020-12-31
| 1 | 25 | 2021-01-01 | 2021-01-01 | First quarter ends
| 2 | 26 | 2021-01-02 | 2021-01-02
| 3 | 27 | 2021-01-03 | 2021-01-03
| 4 | 28 | 2021-01-04 | 2021-01-04
| 5 | 29 | 2021-01-05 | 2021-01-05
| 6 | 30 | 2021-01-06 | 2021-01-06
| 7 | 31 | 2021-01-07 | 2021-01-07
| 8 | 32 | 2021-01-08 | 2021-01-08
| 9 | 33 | 2021-01-09 | 2021-01-09
| 10 | 34 | 2021-01-10 | 2021-01-10
| 11 | 35 | 2021-01-11 | 2021-01-11
| 12 | 36 | 2021-01-12 | 2021-01-12
1 | 13 | 37 | 2021-01-13 | 2021-01-13
2 | 14 | 38 | 2021-01-14 | 2021-01-14
3 | 15 | 39 | 2021-01-15 | 2021-01-15
4 | 16 | 40 | 2021-01-16 | 2021-01-16
5 | 17 | 41 | 2021-01-17 | 2021-01-17
6 | 18 | 42 | 2021-01-18 | 2021-01-18
7 | 19 | 43 | 2021-01-19 | 2021-01-19
8 | 20 | 44 | 2021-01-20 | 2021-01-20
9 | 21 | 45 | 2021-01-21 | 2021-01-21
10 | 22 | 46 | 2021-01-22 | 2021-01-22
11 | 23 | 47 | 2021-01-23 | 2021-01-23
12 | 24 | 48 | 2021-01-24 | 2021-01-24
13 | 25 | 49 | 2021-01-25 | 2021-01-25
14 | 26 | 50 | 2021-01-26 | 2021-01-26 | First half ends
15 | 27 | 51 | 2021-01-27 | 2021-01-27
16 | 28 | 52 | 2021-01-28 | 2021-01-28
17 | 29 | 53 | 2021-01-29 | 2021-01-29
18 | 30 | 54 | 2021-01-30 | 2021-01-30
19 | 31 | 55 | 2021-01-31 | 2021-01-31
20 | 32 | 56 | 2021-02-01 | 2021-02-01
21 | 33 | 57 | 2021-02-02 | 2021-02-02
22 | 34 | 58 | 2021-02-03 | 2021-02-03
23 | 35 | 59 | 2021-02-04 | 2021-02-04
24 | 36 | 60 | 2021-02-05 | 2021-02-05
25 | 37 | 61 | 2021-02-06 | 2021-02-06
26 | 38 | 62 | 2021-02-07 | 2021-02-07
27 | 39 | 63 | 2021-02-08 | 2021-02-08
28 | 40 | 64 | 2021-02-09 | 2021-02-09
29 | 41 | 65 | 2021-02-10 | 2021-02-10
30 | 42 | 66 | 2021-02-11 | 2021-02-11
31 | 43 | 67 | 2021-02-12 | 2021-02-12
32 | 44 | 68 | 2021-02-13 | 2021-02-13
33 | 45 | 69 | 2021-02-14 | 2021-02-14
34 | 46 | 70 | 2021-02-15 | 2021-02-15
35 | 47 | 71 | 2021-02-16 | 2021-02-16
36 | 48 | 72 | 2021-02-17 | 2021-02-17
37 | 49 | 73 | 2021-02-18 | 2021-02-18
38 | 50 | 74 | 2021-02-19 | 2021-02-19
39 | 51 | 75 | 2021-02-20 | 2021-02-20 | Third quarter ends
40 | 52 | 76 | 2021-02-21 | 2021-02-21
41 | 53 | 77 | 2021-02-22 | 2021-02-22
42 | 54 | 78 | 2021-02-23 | 2021-02-23
43 | 55 | 79 | 2021-02-24 | 2021-02-24
44 | 56 | 80 | 2021-02-25 | 2021-02-25
45 | 57 | 81 | 2021-02-26 | 2021-02-26
46 | 58 | 82 | 2021-02-27 | 2021-02-27
47 | 59 | 83 | 2021-02-28 | 2021-02-28
48 | 60 | 84 | 2021-03-01 | 2021-03-01
49 | 61 | 85 | 2021-03-02 | 2021-03-02
50 | 62 | 86 | 2021-03-03 | 2021-03-03
51 | 63 | 87 | 2021-03-04 | 2021-03-04
52 | 64 | 88 | 2021-03-05 | 2021-03-05
53 | 65 | 89 | 2021-03-06 | 2021-03-06
54 | 66 | 90 | 2021-03-07 | 2021-03-07
55 | 67 | 91 | 2021-03-08 | 2021-03-08
56 | 68 | 92 | 2021-03-09 | 2021-03-09
57 | 69 | 93 | 2021-03-10 | 2021-03-10
58 | 70 | 94 | 2021-03-11 | 2021-03-11
59 | 71 | 95 | 2021-03-12 | 2021-03-12
60 | 72 | 96 | 2021-03-13 | 2021-03-13
61 | 73 | 97 | 2021-03-14 | 2021-03-14
62 | 74 | 98 | 2021-03-15 | 2021-03-15
63 | 75 | 99 | 2021-03-16 | 2021-03-16
64 | 76 | 100 | 2021-03-17 | 2021-03-17 | End of first 100 days
65 | 77 |  | 2021-03-18 | 2021-03-18
66 | 78 |  | 2021-03-19 | 2021-03-19
67 | 79 |  | 2021-03-20 | 2021-03-20
68 | 80 |  | 2021-03-21 | 2021-03-21
69 | 81 |  | 2021-03-22 | 2021-03-22
70 | 82 |  | 2021-03-23 | 2021-03-23
71 | 83 |  | 2021-03-24 | 2021-03-24
72 | 84 |  | 2021-03-25 | 2021-03-25
73 | 85 |  | 2021-03-26 | 2021-03-26
74 | 86 |  | 2021-03-27 | 2021-03-27
75 | 87 |  | 2021-03-28 | 2021-03-28
76 | 88 |  | 2021-03-29 | 2021-03-29
77 | 89 |  | 2021-03-30 | 2021-03-30
78 | 90 |  | 2021-03-31 | 2021-03-31
79 | 91 |  | 2021-04-01 | 2021-04-01
80 | 92 |  | 2021-04-02 | 2021-04-02
81 | 93 |  | 2021-04-03 | 2021-04-03
82 | 94 |  | 2021-04-04 | 2021-04-04
83 | 95 |  | 2021-04-05 | 2021-04-05
84 | 96 |  | 2021-04-06 | 2021-04-06
85 | 97 |  | 2021-04-07 | 2021-04-07
86 | 98 |  | 2021-04-08 | 2021-04-08
87 | 99 |  | 2021-04-09 | 2021-04-09
88 | 100 |  | 2021-04-10 | 2021-04-10
89 | 101 |  | 2021-04-11 | 2021-04-11
90 | 102 |  | 2021-04-12 | 2021-04-12
91 | 103 |  | 2021-04-13 | 2021-04-13
92 | 104 |  | 2021-04-14 | 2021-04-14
93 | 105 |  | 2021-04-15 | 2021-04-15
94 | 106 |  | 2021-04-16 | 2021-04-16
95 | 107 |  | 2021-04-17 | 2021-04-17
96 | 108 |  | 2021-04-18 | 2021-04-18
97 | 109 |  | 2021-04-19 | 2021-04-19
98 | 110 |  | 2021-04-20 | 2021-04-20
99 | 111 |  | 2021-04-21 | 2021-04-21
100 | 112 |  | 2021-04-22 | 2021-04-22
Formulas:
Weekday = [Date]

## Committees
Number | Name | Priority | Icon 1 | Icon 2
1 | Building Public Safety | Reimagining Public Safety and Public Accountability
2 | Making Baltimore Equitable | Commit to Equity at the Core of City Services
3 | Prioritizing Our Youth | Expanding Opportunities for All of Baltimore's Youth
4 | Building Public Trust | Establishing Government Accountability from the Top Down
5 | COVID-19 Recovery | Leading an Effective Coronavirus Response for All
6 | Responsible Stewardship of City Resources | Aligning Resources to Ensure Fiscal Stability and Innovation

## Progress Updates
Action # | Action | Date of Update | Description of Update | Status
1 | Building Public Safety | 2020-12-14 | DPW is determining a date to re-launch recycling services. | In progress

## Possible Statuses
Status | Percentage
Incomplete
Complete

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/