## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count
8 | Building Public Safety | Begin implementing a Group Violence Reduction Strategy. | Baltimore Police Department, Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
9 | Building Public Safety | Meet with community leaders and residents around a shared vision for public safety. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
10 | Building Public Safety | Develop a 911 call diversion working group and draft protocol. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
11 | Building Public Safety | Restart the Criminal Justice Coordinating Council underneath the Mayor's Office of Neighborhood Safety and Engagement. | Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
12 | Building Public Safety | Convene the first meeting of the Public Safety Advisory Commission. | Mayor's Office of Neighborhood Safety & Engagement | Complete | 1
1 | Building Public Safety | Create Mayor's Office of Neighborhood Safety and Engagement. | Mayor's Office of Neighborhood Safety & Engagement | Complete | 1
2 | Building Public Safety | Hold PoliceStat meetings every-other-week to build stronger accountability within BPD and improve service delivery. | Baltimore Police Department, Mayor's Office of Performance & Innovation | Complete | 1
3 | Building Public Safety | Set clear, coordinated public safety vision that addresses violence today and root causes. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement, Baltimore City Health Department, Baltimore Police Department | Complete | 1
4 | Building Public Safety | Commit to monthly updates on major consent decree milestones reached and increase community engagement. | Mayor's Office, Baltimore Police Department | Complete | 1
5 | Building Public Safety | Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | Mayor's Office of Neighborhood Safety & Engagement | Complete | 1
6 | Building Public Safety | Develop and rollout a strategy to slow the flow of illegal guns into Baltimore City. | Mayor's Office, Baltimore Police Department | Complete | 1
7 | Building Public Safety | Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | Baltimore City Department of Transportation | Complete | 1
44 | Building Public Trust | Expand who has to file annual financial disclosures. | Baltimore City Ethics Board | Not Yet Started | 1
34 | Building Public Trust | Kick off community engagement plan to introduce City Administrator and other senior officials to public. | Mayor's Office | In Progress | 1
35 | Building Public Trust | Establish, through CitiStat, performance management to ensure greater accountability and more equitable delivery of City services for residents. | Mayor's Office of Performance & Innovation | Complete | 1
37 | Building Public Trust | Announce an action plan to reform Baltimore's water billing system. | Baltimore City Department of Public Works | In Progress | 1
38 | Building Public Trust | Appoint a permanent Department of Public Works Director. | Baltimore City Department of Public Works | Complete | 1
39 | Building Public Trust | Appoint a permanent Housing Commissioner. | Mayor's Office | In Progress | 1
40 | Building Public Trust | Appoint a permanent Homeless Services Director. | Mayor's Office of Homeless Services | In Progress | 1
41 | Building Public Trust | Initiate a process to remove the backlog of transportation and infrastructure related 311 service requests in historically marginalized communities. | Baltimore City Department of Public Works, Baltimore City Department of Transportation | In Progress | 1
42 | Building Public Trust | Initiate a process improvement project to establish a more seamless system for applying for and receiving city-owned properties. | Mayor's Office | In Progress | 1
43 | Building Public Trust | Make stronger commitments to cleaning up sewage backups. | Baltimore City Department of Public Works | Complete | 1
33 | Building Public Trust | Hire Baltimore's first City Administrator. | Mayor's Office | Complete | 1
36 | Building Public Trust | Restore recycling services, which were suspended due to COVID-19. | Baltimore City Department of Public Works | Complete | 1
46 | COVID-19 Recovery | Create a dashboard to track CARES act funding to ensure equitable distribution. | Baltimore City Department of Finance | Not Yet Started | 1
47 | COVID-19 Recovery | Use Rapid Rehousing dollars to move additional people and families experiencing homelessness to more permanent housing. | Mayor's Office of Homeless Services | In Progress | 1
50 | COVID-19 Recovery | Identify clear point of contact for local businesses to more effectively navigate city government. | Mayor's Office, Baltimore Development Corporation | In Progress | 1
51 | COVID-19 Recovery | Deploy $6 million in direct support for families impacted by COVID-19. | Mayor's Office of Children and Family Success | In Progress | 1
52 | COVID-19 Recovery | Expand Baltimore's eviction prevention efforts. | Baltimore City Department of Housing and Community Development, Mayor's Office of Children and Family Success | In Progress | 1
45 | COVID-19 Recovery | Develop and communicate a COVID-19 vaccination prioritization strategy. | Baltimore City Health Department | Complete | 1
48 | COVID-19 Recovery | Extend emergency shelter in local hotels when CARES Act funding expires. | Mayor's Office of Homeless Services | Complete | 1
49 | COVID-19 Recovery | Cap restaurant delivery fees on third-party app services. | Baltimore City Department of Finance | Complete | 1
53 | COVID-19 Recovery | Implement the COVID-19: Prevention, Control, and Support strategy to mitigate the disproportionate impact the pandemic on the Latino community. | Baltimore City Health Department, Mayor's Office of Immigrant Affairs | Complete | 1
18 | Making Baltimore Equitable | Elevate Sustainability Director to a cabinet-level position. | Mayor's Office, Baltimore City Department of Planning | In Progress | 1
21 | Making Baltimore Equitable | Activate small and local business preference in the procurement process. | Baltimore City Department of Finance, Baltimore City Bureau of Procurement | Not Yet Started | 1
14 | Making Baltimore Equitable | Hire a Digital Equity Director. | Mayor's Office | Complete | 1
15 | Making Baltimore Equitable | Make Baltimore City’s hiring practices more equitable. | Baltimore City Department of Human Resources | In Progress | 1
16 | Making Baltimore Equitable | Identify a senior official in each agency to be responsible for equity. | Mayor's Office | In Progress | 1
17 | Making Baltimore Equitable | Commit to moving Baltimore towards zero waste and begin making shifts toward a more sustainable city. | Mayor's Office, Baltimore City Department of Planning and Baltimore City Department of Public Works | In Progress | 1
19 | Making Baltimore Equitable | Create improved transparency into the retention, attraction, and growth of City neighborhoods. | Baltimore City Department of Housing & Community Development, Baltimore City Department of Planning, Baltimore City Department of Finance | In Progress | 1
22 | Making Baltimore Equitable | Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | Mayor's Office of Employment Development, Baltimore Development Corporation | In Progress | 1
23 | Making Baltimore Equitable | Establish a Hiring Task Force to review HR practices to meet equity requirements and continue to professionalize our workforce. | Baltimore City Department of Human Resources | In Progress | 1
24 | Making Baltimore Equitable | Prioritize the Baltimore Greenway Trails Network. | Baltimore City Department of Planning, Baltimore City Department of Transportation, Baltimore City Department of Recreation & Parks | In Progress | 1
13 | Making Baltimore Equitable | Hire Baltimore's first Chief Equity Officer. | Mayor's Office, Baltimore City Office of Equity & Civil Rights | Complete | 1
20 | Making Baltimore Equitable | Initiate a full reform of the procurement process. | Baltimore City Department of Finance, Baltimore City Bureau of Procurement | Complete | 1
25 | Making Baltimore Equitable | Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | Baltimore City Department of Planning | Complete | 1
29 | Prioritizing Our Youth | Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | Baltimore City Department of Recreation & Parks | In Progress | 1
30 | Prioritizing Our Youth | Partner with the Youth Commission to establish cabinet member youth shadows. | Baltimore City Youth Commission, Mayor's Office of Children and Family Success | In Progress | 1
32 | Prioritizing Our Youth | Host biannual Youth Summits with the Mayor to bring attention to youth-focused issues in the City. | Mayor's Office of Children and Family Success | In Progress | 1
26 | Prioritizing Our Youth | Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | Mayor's Office, Maryland General Assembly | In Progress | 1
27 | Prioritizing Our Youth | Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | Mayor's Office of Employment Development | In Progress | 1
28 | Prioritizing Our Youth | Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | Mayor's Office of Children and Family Success, Baltimore City Health Department | Complete | 1
31 | Prioritizing Our Youth | Join Mayors for Guaranteed Income with a focus on supporting youth and families. | Mayor's Office of Children and Family Success | Complete | 1
55 | Responsible Stewardship of City Resources | Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | Baltimore City Department of Finance | Not Yet Started | 1
54 | Responsible Stewardship of City Resources | Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | Baltimore City Department of Planning | In Progress | 1
56 | Responsible Stewardship of City Resources | Expand community engagement in the budget process. | Baltimore City Department of Finance | In Progress | 1
57 | Responsible Stewardship of City Resources | Commit to updating the City's 10-year financial plan. | Baltimore City Department of Finance | In Progress | 1
58 | Responsible Stewardship of City Resources | Design and release Open Checkbook for Baltimore to increase transparency and accountability. | Baltimore City Information & Technology, Baltimore City Department of Finance | In Progress | 1

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
0 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
1 | 2020-12-09 | 2020-12-09
2 | 2020-12-10 | 2020-12-10
3 | 2020-12-11 | 2020-12-11
4 | 2020-12-12 | 2020-12-12
5 | 2020-12-13 | 2020-12-13
6 | 2020-12-14 | 2020-12-14
7 | 2020-12-15 | 2020-12-15
8 | 2020-12-16 | 2020-12-16
9 | 2020-12-17 | 2020-12-17
10 | 2020-12-18 | 2020-12-18
11 | 2020-12-19 | 2020-12-19
12 | 2020-12-20 | 2020-12-20
13 | 2020-12-21 | 2020-12-21
14 | 2020-12-22 | 2020-12-22
15 | 2020-12-23 | 2020-12-23
16 | 2020-12-24 | 2020-12-24
17 | 2020-12-25 | 2020-12-25
18 | 2020-12-26 | 2020-12-26
19 | 2020-12-27 | 2020-12-27
20 | 2020-12-28 | 2020-12-28
21 | 2020-12-29 | 2020-12-29
22 | 2020-12-30 | 2020-12-30
23 | 2020-12-31 | 2020-12-31
24 | 2021-01-01 | 2021-01-01 | First quarter ends
25 | 2021-01-02 | 2021-01-02
26 | 2021-01-03 | 2021-01-03
27 | 2021-01-04 | 2021-01-04
28 | 2021-01-05 | 2021-01-05
29 | 2021-01-06 | 2021-01-06
30 | 2021-01-07 | 2021-01-07
31 | 2021-01-08 | 2021-01-08
32 | 2021-01-09 | 2021-01-09
33 | 2021-01-10 | 2021-01-10
34 | 2021-01-11 | 2021-01-11
35 | 2021-01-12 | 2021-01-12
36 | 2021-01-13 | 2021-01-13
37 | 2021-01-14 | 2021-01-14
38 | 2021-01-15 | 2021-01-15
39 | 2021-01-16 | 2021-01-16
40 | 2021-01-17 | 2021-01-17
41 | 2021-01-18 | 2021-01-18
42 | 2021-01-19 | 2021-01-19
43 | 2021-01-20 | 2021-01-20
44 | 2021-01-21 | 2021-01-21
45 | 2021-01-22 | 2021-01-22
46 | 2021-01-23 | 2021-01-23
47 | 2021-01-24 | 2021-01-24
48 | 2021-01-25 | 2021-01-25
49 | 2021-01-26 | 2021-01-26 | First half ends
50 | 2021-01-27 | 2021-01-27
51 | 2021-01-28 | 2021-01-28
52 | 2021-01-29 | 2021-01-29
53 | 2021-01-30 | 2021-01-30
54 | 2021-01-31 | 2021-01-31
55 | 2021-02-01 | 2021-02-01
56 | 2021-02-02 | 2021-02-02
57 | 2021-02-03 | 2021-02-03
58 | 2021-02-04 | 2021-02-04
59 | 2021-02-05 | 2021-02-05
60 | 2021-02-06 | 2021-02-06
61 | 2021-02-07 | 2021-02-07
62 | 2021-02-08 | 2021-02-08
63 | 2021-02-09 | 2021-02-09
64 | 2021-02-10 | 2021-02-10
65 | 2021-02-11 | 2021-02-11
66 | 2021-02-12 | 2021-02-12
67 | 2021-02-13 | 2021-02-13
68 | 2021-02-14 | 2021-02-14
69 | 2021-02-15 | 2021-02-15
70 | 2021-02-16 | 2021-02-16
71 | 2021-02-17 | 2021-02-17
72 | 2021-02-18 | 2021-02-18
73 | 2021-02-19 | 2021-02-19
74 | 2021-02-20 | 2021-02-20 | Third quarter ends
75 | 2021-02-21 | 2021-02-21
76 | 2021-02-22 | 2021-02-22
77 | 2021-02-23 | 2021-02-23
78 | 2021-02-24 | 2021-02-24
79 | 2021-02-25 | 2021-02-25
80 | 2021-02-26 | 2021-02-26
81 | 2021-02-27 | 2021-02-27
82 | 2021-02-28 | 2021-02-28
83 | 2021-03-01 | 2021-03-01
84 | 2021-03-02 | 2021-03-02
85 | 2021-03-03 | 2021-03-03
86 | 2021-03-04 | 2021-03-04
87 | 2021-03-05 | 2021-03-05
88 | 2021-03-06 | 2021-03-06
89 | 2021-03-07 | 2021-03-07
90 | 2021-03-08 | 2021-03-08
91 | 2021-03-09 | 2021-03-09
92 | 2021-03-10 | 2021-03-10
93 | 2021-03-11 | 2021-03-11
94 | 2021-03-12 | 2021-03-12
95 | 2021-03-13 | 2021-03-13
96 | 2021-03-14 | 2021-03-14
97 | 2021-03-15 | 2021-03-15
98 | 2021-03-16 | 2021-03-16
99 | 2021-03-17 | 2021-03-17
100 | 2021-03-18 | 2021-03-18 | End of first 100 days
101 | 2021-03-19 | Fri
102 | 2021-03-20 | Sat
103 | 2021-03-21 | Sun
104 | 2021-03-22 | Mon
105 | 2021-03-23 | Tue
106 | 2021-03-24 | Wed
107 | 2021-03-25 | Thu
108 | 2021-03-26 | Fri
109 | 2021-03-27 | Sat
110 | 2021-03-28 | Sun
111 | 2021-03-29 | Mon
112 | 2021-03-30 | Tue
113 | 2021-03-31 | Wed
114 | 2021-04-01 | Thu
115 | 2021-04-02 | Fri
116 | 2021-04-03 | Sat
117 | 2021-04-04 | Sun
118 | 2021-04-05 | Mon
119 | 2021-04-06 | Tue
120 | 2021-04-07 | Wed
121 | 2021-04-08 | Thu
122 | 2021-04-09 | Fri
123 | 2021-04-10 | Sat
124 | 2021-04-11 | Sun
125 | 2021-04-12 | Mon
126 | 2021-04-13 | Tue
127 | 2021-04-14 | Wed
128 | 2021-04-15 | Thu
129 | 2021-04-16 | Fri
130 | 2021-04-17 | Sat
131 | 2021-04-18 | Sun
132 | 2021-04-19 | Mon
133 | 2021-04-20 | Tue
134 | 2021-04-21 | Wed
135 | 2021-04-22 | Thu
136 | 2021-04-23 | Fri
137 | 2021-04-24 | Sat
138 | 2021-04-25 | Sun
139 | 2021-04-26 | Mon
140 | 2021-04-27 | Tue
141 | 2021-04-28 | Wed
142 | 2021-04-29 | Thu
143 | 2021-04-30 | Fri
144 | 2021-05-01 | Sat
145 | 2021-05-02 | Sun
146 | 2021-05-03 | Mon
147 | 2021-05-04 | Tue
148 | 2021-05-05 | Wed
149 | 2021-05-06 | Thu
150 | 2021-05-07 | Fri
151 | 2021-05-08 | Sat
152 | 2021-05-09 | Sun
153 | 2021-05-10 | Mon
154 | 2021-05-11 | Tue
155 | 2021-05-12 | Wed
156 | 2021-05-13 | Thu
157 | 2021-05-14 | Fri
158 | 2021-05-15 | Sat
159 | 2021-05-16 | Sun
160 | 2021-05-17 | Mon
161 | 2021-05-18 | Tue
162 | 2021-05-19 | Wed
163 | 2021-05-20 | Thu
164 | 2021-05-21 | Fri
165 | 2021-05-22 | Sat
166 | 2021-05-23 | Sun
167 | 2021-05-24 | Mon
168 | 2021-05-25 | Tue
169 | 2021-05-26 | Wed
170 | 2021-05-27 | Thu
171 | 2021-05-28 | Fri
172 | 2021-05-29 | Sat
173 | 2021-05-30 | Sun
174 | 2021-05-31 | Mon
175 | 2021-06-01 | Tue
176 | 2021-06-02 | Wed
177 | 2021-06-03 | Thu
178 | 2021-06-04 | Fri
179 | 2021-06-05 | Sat
180 | 2021-06-06 | Sun
181 | 2021-06-07 | Mon
182 | 2021-06-08 | Tue
183 | 2021-06-09 | Wed
184 | 2021-06-10 | Thu
185 | 2021-06-11 | Fri
186 | 2021-06-12 | Sat
187 | 2021-06-13 | Sun
188 | 2021-06-14 | Mon
189 | 2021-06-15 | Tue
190 | 2021-06-16 | Wed
191 | 2021-06-17 | Thu
192 | 2021-06-18 | Fri
193 | 2021-06-19 | Sat
194 | 2021-06-20 | Sun
195 | 2021-06-21 | Mon
196 | 2021-06-22 | Tue
197 | 2021-06-23 | Wed
198 | 2021-06-24 | Thu
199 | 2021-06-25 | Fri
200 | 2021-06-26 | Sat
201 | 2021-06-27 | Sun
202 | 2021-06-28 | Mon
203 | 2021-06-29 | Tue
204 | 2021-06-30 | Wed
205 | 2021-07-01 | Thu
206 | 2021-07-02 | Fri
207 | 2021-07-03 | Sat
208 | 2021-07-04 | Sun
209 | 2021-07-05 | Mon
210 | 2021-07-06 | Tue
211 | 2021-07-07 | Wed
212 | 2021-07-08 | Thu
213 | 2021-07-09 | Fri
214 | 2021-07-10 | Sat
215 | 2021-07-11 | Sun
216 | 2021-07-12 | Mon
217 | 2021-07-13 | Tue
218 | 2021-07-14 | Wed
219 | 2021-07-15 | Thu
220 | 2021-07-16 | Fri
221 | 2021-07-17 | Sat
222 | 2021-07-18 | Sun
223 | 2021-07-19 | Mon
224 | 2021-07-20 | Tue
225 | 2021-07-21 | Wed
226 | 2021-07-22 | Thu
227 | 2021-07-23 | Fri
228 | 2021-07-24 | Sat
229 | 2021-07-25 | Sun
230 | 2021-07-26 | Mon
231 | 2021-07-27 | Tue
232 | 2021-07-28 | Wed
233 | 2021-07-29 | Thu
234 | 2021-07-30 | Fri
235 | 2021-07-31 | Sat
236 | 2021-08-01 | Sun
237 | 2021-08-02 | Mon
238 | 2021-08-03 | Tue
239 | 2021-08-04 | Wed
240 | 2021-08-05 | Thu
241 | 2021-08-06 | Fri
242 | 2021-08-07 | Sat
243 | 2021-08-08 | Sun
244 | 2021-08-09 | Mon
245 | 2021-08-10 | Tue
246 | 2021-08-11 | Wed
247 | 2021-08-12 | Thu
248 | 2021-08-13 | Fri
249 | 2021-08-14 | Sat
250 | 2021-08-15 | Sun
251 | 2021-08-16 | Mon
252 | 2021-08-17 | Tue
253 | 2021-08-18 | Wed
254 | 2021-08-19 | Thu
255 | 2021-08-20 | Fri
256 | 2021-08-21 | Sat
257 | 2021-08-22 | Sun
258 | 2021-08-23 | Mon
259 | 2021-08-24 | Tue
260 | 2021-08-25 | Wed
261 | 2021-08-26 | Thu
262 | 2021-08-27 | Fri
263 | 2021-08-28 | Sat
264 | 2021-08-29 | Sun
265 | 2021-08-30 | Mon
266 | 2021-08-31 | Tue
267 | 2021-09-01 | Wed
268 | 2021-09-02 | Thu
269 | 2021-09-03 | Fri
270 | 2021-09-04 | Sat
271 | 2021-09-05 | Sun
272 | 2021-09-06 | Mon
273 | 2021-09-07 | Tue
274 | 2021-09-08 | Wed
275 | 2021-09-09 | Thu
276 | 2021-09-10 | Fri
277 | 2021-09-11 | Sat
278 | 2021-09-12 | Sun
279 | 2021-09-13 | Mon
280 | 2021-09-14 | Tue
281 | 2021-09-15 | Wed
282 | 2021-09-16 | Thu
283 | 2021-09-17 | Fri
284 | 2021-09-18 | Sat
285 | 2021-09-19 | Sun
286 | 2021-09-20 | Mon
287 | 2021-09-21 | Tue
288 | 2021-09-22 | Wed
289 | 2021-09-23 | Thu
290 | 2021-09-24 | Fri
291 | 2021-09-25 | Sat
292 | 2021-09-26 | Sun
293 | 2021-09-27 | Mon
294 | 2021-09-28 | Tue
295 | 2021-09-29 | Wed
296 | 2021-09-30 | Thu
297 | 2021-10-01 | Fri
298 | 2021-10-02 | Sat
299 | 2021-10-03 | Sun
300 | 2021-10-04 | Mon
301 | 2021-10-05 | Tue
302 | 2021-10-06 | Wed
303 | 2021-10-07 | Thu
304 | 2021-10-08 | Fri
305 | 2021-10-09 | Sat
306 | 2021-10-10 | Sun
307 | 2021-10-11 | Mon
308 | 2021-10-12 | Tue
309 | 2021-10-13 | Wed
310 | 2021-10-14 | Thu
311 | 2021-10-15 | Fri
312 | 2021-10-16 | Sat
313 | 2021-10-17 | Sun
314 | 2021-10-18 | Mon
315 | 2021-10-19 | Tue
316 | 2021-10-20 | Wed
317 | 2021-10-21 | Thu
318 | 2021-10-22 | Fri
319 | 2021-10-23 | Sat
320 | 2021-10-24 | Sun
321 | 2021-10-25 | Mon
322 | 2021-10-26 | Tue
323 | 2021-10-27 | Wed
324 | 2021-10-28 | Thu
325 | 2021-10-29 | Fri
326 | 2021-10-30 | Sat
327 | 2021-10-31 | Sun
328 | 2021-11-01 | Mon
329 | 2021-11-02 | Tue
330 | 2021-11-03 | Wed
331 | 2021-11-04 | Thu
332 | 2021-11-05 | Fri
333 | 2021-11-06 | Sat
334 | 2021-11-07 | Sun
335 | 2021-11-08 | Mon
336 | 2021-11-09 | Tue
337 | 2021-11-10 | Wed
338 | 2021-11-11 | Thu
339 | 2021-11-12 | Fri
340 | 2021-11-13 | Sat
341 | 2021-11-14 | Sun
342 | 2021-11-15 | Mon
343 | 2021-11-16 | Tue
344 | 2021-11-17 | Wed
345 | 2021-11-18 | Thu
346 | 2021-11-19 | Fri
347 | 2021-11-20 | Sat
348 | 2021-11-21 | Sun
349 | 2021-11-22 | Mon
350 | 2021-11-23 | Tue
351 | 2021-11-24 | Wed
352 | 2021-11-25 | Thu
353 | 2021-11-26 | Fri
354 | 2021-11-27 | Sat
355 | 2021-11-28 | Sun
356 | 2021-11-29 | Mon
357 | 2021-11-30 | Tue
358 | 2021-12-01 | Wed
359 | 2021-12-02 | Thu
360 | 2021-12-03 | Fri
361 | 2021-12-04 | Sat
362 | 2021-12-05 | Sun
363 | 2021-12-06 | Mon
364 | 2021-12-07 | Tue
365 | 2021-12-08 | Wed
366 | 2021-12-09 | Thu
367 | 2021-12-10 | Fri
368 | 2021-12-11 | Sat
369 | 2021-12-12 | Sun
370 | 2021-12-13 | Mon
371 | 2021-12-14 | Tue
372 | 2021-12-15 | Wed
373 | 2021-12-16 | Thu
374 | 2021-12-17 | Fri
375 | 2021-12-18 | Sat
376 | 2021-12-19 | Sun
377 | 2021-12-20 | Mon
378 | 2021-12-21 | Tue
379 | 2021-12-22 | Wed
380 | 2021-12-23 | Thu
381 | 2021-12-24 | Fri
382 | 2021-12-25 | Sat
383 | 2021-12-26 | Sun
384 | 2021-12-27 | Mon
385 | 2021-12-28 | Tue
386 | 2021-12-29 | Wed
387 | 2021-12-30 | Thu
388 | 2021-12-31 | Fri
Formulas:
Weekday = [Date]

## Committees
Number | Name | Priority
1 | Building Public Safety | Reimagining Public Safety and Public Accountability
2 | Making Baltimore Equitable | Commit to Equity at the Core of City Services
3 | Prioritizing Our Youth | Expanding Opportunities for All of Baltimore's Youth
4 | Building Public Trust | Establishing Government Accountability from the Top Down
5 | COVID-19 Recovery | Leading an Effective Coronavirus Response for All
6 | Responsible Stewardship of City Resources | Aligning Resources to Ensure Fiscal Stability and Innovation

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/